## Schedule
| Client name Client address | Toby Rapp Construction Toby Rapp 503.740.4862 tobyrapp@comcast.net www.tobyrapp.com ccb 94829 |  | 2010-02-25 | time axis 2010-04-12 to 2010-05-28
updated May 2, 2010
| what? | who? | days
0 | sign paperwork | owner & TRC |  | 25%
0 | permits | electrician to get plumber to get | bar: 2010-04-12
0 | identify fixture models, surfaces, & colors | owner | bar: 2010-04-12
 | 3 piece neo angle shower, shower door, shower trim kit (this is the handle), valve and shower head
 | Vanity with attached counter top, sink and faucets
 | Wall cabinet or shelves
 | Floor tile and cove base
 | 80 cfm fan
 | Lighting
 | Paint color (prefer paint from Sherwin Williams, but any brand will do)
 | Paint grade louvered bi fold doors (forgot to measure, let TRC know if needed to stop by and do this)
 | Any bath accessories you’d like TRC to install
1 | Demo bath room/spray closet doors | TRC | 1 | bar: 2010-04-12
A.1 | Mold Found |  | 1 | bar: 2010-04-13
2 | Plumber and electrician x2 days | TRC | 2 | bar: 2010-04-14 to 2010-04-15
A.5/6 | Re-Pipe and Complex Plumbing Required | TRC | 2 | bar: 2010-04-16; 2010-04-19
3 | Inspections/Closet work | TRC | 1 | bar: 2010-04-20
4 | Insulate/inspection/get closet ready for rock | TRC | 1 |  | 2010-04-20: 25%; 2010-04-21: 
B.1 | Re-Pipe kitchen & main bath | TRC | 1 | bar: 2010-04-21 to 2010-04-23
B.1 | Plumbing Inspection | TRC | 1 | bar: 2010-04-26
5 C.3 | Sheetrock x4 days & Closet Ceiling Alignment | TRC | 5 | bar: 2010-04-27 to 2010-04-30; 2010-05-03
A.2 C.1 | Tile in Shower & Shower Tile Selection | TRC | 7 | bar: 2010-04-23; 2010-04-26 to 2010-04-30; 2010-05-03
C.2 | Rise in concrete | TRC | 1 | bar: 2010-04-30
6 | Set trim (bath & closet), paint walls & tile bath floor | TRC | 1 |  | 2010-05-03: 25%
7 | Set vanity cab | TRC | 1 | bar: 2010-05-04
8 | Grout floor/set closet door | TRC | 1 | bar: 2010-05-05
9 | Finish paint | TRC | 1 | bar: 2010-05-06
10 | Set finish plumbing | TRC | 1 | bar: 2010-05-05
C.4 | Set finish electrical | TRC | 1 | bar: 2010-05-10
11 | Install accessories | TRC | 1 | bar: 2010-05-07
C.4 | Touch up & clean up | TRC | 4 | bar: 2010-05-11 to 2010-05-14
| TRC vacation | TRC | 5 |  | 2010-05-10: TRC vacation
D.1 | Shower Door Install | TRC | 1 | bar: 2010-05-18; 2010-05-26
12 | Complete | TRC
% amounts correspond to the TRC payment schedule and amounts due
original end date

## Scope
Client name Client address |  |  |  | Toby Rapp Construction Toby Rapp 503.740.4862 tobyrapp@comcast.net www.tobyrapp.com ccb 94829
Changes after initial bid signed |  | updated May 2, 2010 |  | T&M = Time & Materials
| Item | Description | Resolution | Cost | Date Identified
A.1 | Mold Found | floor wasn't properly vented & caused mold in the walls | Removing the laundry room floor vent. Replacing the sheetrock. | TRC to provide by April 21 after sheetrocker reviews it | 2010-04-12
A.2 | Tile in shower | switched from a fiberglass shower to tile in shower | Lorilee & Kent to pick tiles and include a 'layout map' if needed to TRC by April 20. Niche shelf will be included TRC to return the fiberglass shower. | T&M | 2010-04-13
A.3 | Additional Light/Switch | light & light switch added to bathroom | Add it | T&M (electrical is already T&M) | 2010-04-13
A.4 | Blowdryer Shelf | added blowdryer shelf | Lorilee & Kent to tell TRC final design by April 21 | T&M | 2010-04-13
A.5 | Re-Pipe | re-piped the main floor tub & hose bib | completed by plumber while pipes exposed | T&M (~2 hrs additional time) | 2010-04-13
A.6 | Complex Plumbing Required | once walls were opened, the existing plumbing was much more complex then expected, so more time needed to complete it | plumber continued the plumbing until complete | T&M (~4 hrs additional time) | 2010-04-13
B.1 | Re-Pipe kitchen & main bath | Replace existing galvanized pipe at kitchen, main bath, and master bath sink. New water line to interior filter. Done to improve water quality & pressure. | complete the change | approximately $2350. The corresponding bid for this change has $2200, but the master bath sink was added. | 2010-04-21
C.1 | Shower Tile Selection | Tile selected wouldn't work for the project. | Caused a delay of 1-2 days. Hoping to have it complete Monday May 3rd which is a one day delay. | part of A.2, so will be part of that T&M. It did add to the 'time' component | 2010-04-27
C.2 | Rise in concrete | Unexpected rise in the concrete which needs to be chipped down and filled. | complete the change | T&M (~4 hrs additional time) | 2010-04-30
C.3 | Closet Ceiling Alignment | Closet ceiling didn't align between the old and new sections. | Sheetrocker to apply extra mud to make it level which requires more time to dry. | no extra cost, just an extra day in the schedule | 2010-04-30
C.4 | Finish & Clean up | Finish & clean up | Due to the previous changes, need to shift out the finish electrical & allow time for proper clean up | no extra cost, just extra days in the schedule | 2010-04-30
D.1 | Shower Door incorrect size | Shower Door was delivered the wrong size | TRC to work with George Morlan to get a correct one expedited | no extra cost, just extra days in the schedule | 2010-05-19

## Budget
| Client name Client address |  |  |  |  | Toby Rapp Construction Toby Rapp 503.740.4862 tobyrapp@comcast.net www.tobyrapp.com ccb 94829
updated May 2, 2010
Items marked as 'allowance' or estimate will change over from the time of signing the bid and the final bill. Please contact us if you have questions
| DESCRIPTION | Qty | Cost | Total | Bid | Comments / Instructions
1 | Demo existing bathroom as needed | 1 | 480 | 480 | 480
2 | Plumb bathroom, new water lines and cleaned drain (no fixtures) | 1 | 1470 | 1470 | 1470
3 | Electrical supplies (plugs, switch, timer gfi and wire) | 1 | 144 | 144 | 144
4 | Electrical as needed | 6 | 101.666 | 609.996 | 609.996
5 | 80 cfm fan (allowance) | 1 | 120 | 120 | 120 | estimate
6 | Install new 80 cfm fan on timer (per code) | 1 | 120 | 120 | 120
7 | Concrete repair as needed | 1 | 90 | 90 | 90
8 | Insulation as needed | 1 | 120 | 120 | 120
9 | Sheetrock bathroom (all new rock over bare studs) | 1 | 840 | 840 | 840
10 | Paint bathroom | 1 | 300 | 300 | 300
11 | Corner (neo angle) shower stall white (min) | 1 | 0 | 0 | 609 | removed because switched to tile in shower (A.2)
12 | Neo angle shower doors (min) | 1 | 200 | 200 | 576 | less due to tile in shower change (A.2)
13 | shelving (allowance) | 1 | 300 | 300 | 300 | estimate
14 | New vanity with molded countertop/sink (allowance) | 1 | 540 | 540 | 540 | estimate
15 | Shower head/valve/trim kit and sink faucet (allowance) | 1 | 600 | 600 | 600 | estimate
16 | Tile flooring (includes $3 per sq ft tile allowance) | 56 | 13.1429 | 736.0002 | 736.0002 | estimate
Closet
17 | Demo existing closet wall and move flush with bedroom wall | 1 | 180 | 180 | 180
18 | BiFold closet doors (primed full louver, + 10 for half louver) | 1 | 355 | 355 | 355
19 | Repair and/or replace trim at door | 1 | 90 | 90 | 90
20 | Sheetrock | 1 | 360 | 360 | 360
21 | New florescent light to meet code | 1 | 90 | 90 | 90
22 | Electrical supplies (wire & switch) | 1 | 54 | 54 | 54
23 | Electrical for new light (allowance) | 2.5 | 101 | 252.5 | 252.5
24 | Repair floor | 1 | 120 | 120 | 120 | estimate
25 | Paint | 1 | 120 | 120 | 120
26 | Labor, clean up and waste disposal | 1 | 780 | 780 | 780
27 | Permits $150 - $250 | 1 | 200 | 200 | 200 | estimate
|  |  | subtotal of above costs | 9271.4962 | 10256.4962
Changes
A.1 | Mold Found | 1 | 200 | 200 |  | estimate
A.2 | Tile in shower | 1 | 1500 | 1500 |  | estimate
A.3 | Additional Light/Switch | 1 | 180 | 180 |  | estimate
A.4 | Blowdryer Shelf | 1 |  | 0 |  | do not know design
A.5 | Re-Pipe | 1 | 140 | 140 |  | estimate (plumber to provide final)
A.6 | Complex Plumbing Required | 1 | 280 | 280 | 2300 | estimate
B.1 | re-pipe kitchen | 1 | 400 | 400 |  | all managed and paid for under separate invoice/contract
B.1 | re-pipe garage area | 1 | 600 | 600
B.1 | demo for kitchen pipe | 1 | 150 | 150
B.1 | demo garage area | 1 | 200 | 200
B.1 | sheetrock for kitchen repipe | 1 | 225 | 225
B.1 | sheetrock for garage area | 1 | 150 | 150
B.1 | waste disposal and dump fee | 1 | 100 | 100
B.1 | TRC markup | 1 | 275 | 275
B.1 | approximate cost of permits | 1 | 100 | 100
B.1 | re-pipe master bath sink | 1 | 150 | 150 | 2350
C.1 | Shower Tile Selection | 1 | 0 | 0 |  | part of A.2, but this item caused extra time
C.2 | Rise in concrete | 1 | 200 | 200
C.3 | Closet Ceiling Alignment | 1 | 0 | 0
C.4 | Finish & Clean up | 1 | 0 | 0 | 200
|  |  | subtotal of above costs | 4850
| GRAND TOTAL to you |  |  | 14121.4962
|  |  |  | -2350 | deducting re-pipe work which was managed under separate invoice/contract
| TOTAL (original contract) |  |  | 11771.4962
|  |  |  | 3865 | variance between bid and current estimated bid
Payments |  | est. date | actual date | est. amount | actual amount | approximate amount remaining
| 25% at bid signing | 2010-03-12 | 2010-03-12 | 2500 | 2500 | 11621.4962
| 25% payment after inspections | 2010-04-20 | 2010-04-20 | 2500 | 2500 | 9121.4962
| B.1 Change | 2010-04-26 | 2010-04-26 | 1100 | 1100 | 8021.4962
| B.1 change balance after sheetrock | 2010-05-03 | 2010-05-03 | 1250 | 1250 | 6771.4962
| 25% after sheetrock | 2010-05-03 | 2010-05-03 | 2500 | 2500 | 4271.4962
| 20% after finish plumbing & electrical | 2010-05-17 |  | 2000 |  | 2271.4962
| final amount (5% + changes) after agreed complete | 2010-05-17 |  | 2271.4962 |  | 0